## Product_Backlog
Product Name:	Robbie Robot Shop					Fields in blue expect your input!
Team ID:

Name:	Katherine Younke
Initials:	KY
Student ID:	1000755371

Total Features	Left	Available	Completed	Sprint Ends
Total at Start	92	92
Sprint 1	92	16	16	Mar 28
Sprint 2	76	9	6	Apr 04
Sprint 3	70	38	12	Apr 11
Sprint 4	58	29	0	Apr 18
Sprint 5	44	0	0	Apr 25
Sprint 6	44	0	0	May 02

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Sprint # (by team size)					Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Actual Sprint #	1	2	3	4	Pts	Cml	As a...	I want to...	So that...	Type	Notes
Create_Parts	1	COMPLETE		1	1	1	1	21	21	PM	create robot parts	I can define robot models	CLI	No menu required here – run program, create a part
Create_Models	2	COMPLETE		2	1	1	1	13	34	PM	define new robot models	RRS can sell them to our Beloved Customers	CLI	Menu needed – create parts, then create a robot model
Calculate_Model_Fields	2.5	NS					Calculate total weight, cost of parts, power limited, battery life, and speed	I can show customers, s.a, p.m, and boss all values in a model	CLI
Browse_Catalog	3	NS		2	1	1	1	5	39	BC	browse a catalog of robot models	I can buy one or more robots	CLI	Need to list robots models, then list parts in selected model
New_Customer	4	NS		3	2	1	1	3	42	PB	create a new Beloved Customer	I can keep track of who's buying our products	CLI	The usual name, customer number, phone number, and email address
New_Associate	5	NS		3	2	1	1	3	45	PB	create a new Sales Associate	I can keep track of my employees' performance	CLI	Name and employee number at a minimum
New_Orders	6	NS		3	2	2	1	8	53	SA	create a robot order for a Customer	I can sell robots and thus do my job well	CLI	Select robot model and quantity, show details with total price
Save_History	7	NS		3	2	2	2	13	66	PB	ensure persistence of the RRS data	we don't lose orders or historical data	CLI	(CLI) Write the data to the default filename and reload it next time the program runs
GUI_Window	8	NS		4	3	2	2	3	69	All	open a GUI main window	I can interact with RRS Manager with my mouse	GUI	No menu required here – run program, create a part
Parts_GUI	9	NS		4	3	2	2	34	103	PM	create robot parts via GUI dialogs	I can define robot models	GUI	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
Models_GUI	10	NS		5	4	3	3	21	124	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	GUI	Similar to robot parts (perhaps Create > Robot Model)
Catalog_GUI	11	NS		6	4	3	3	8	132	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	GUI	A text output is OK initially, but an attractive HTML-like output is desired (perhaps Report > All Robot Models)
	12	NS			5	4	3	21	153	SA	create a robot order for a Customer via GUI	I can sell robots and thus do my job well	GUI	As with CLI (and you’ll need the CLI to add BC and SA people)
	13	NS			5	4	4	13	166	PB	manage a robot order for a Customer via GUI	I can ensure the robot is built and ships	GUI	This will involve a state machine implementation
	14	NS			5	4	4	8	174	PB	create a new Beloved Customer via GUI	I can keep track of who's buying our products	GUI	The usual name, address, phone number, and email address (perhaps Create > Customer)
	15	NS			5	4	4	5	179	PB	create a new Sales Associate via GUI	I can keep track of my employees' performance	GUI	Name and employee number at a minimum (perhaps Create > Sales Associate)
	16	NS			6	5	4	13	192	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	GUI	Add picture when defining robot model, and show it in the robot model report
	17	NS			6	5	4	5	197	PB	allow the users to save data explicitly via GUI	we can save data without exiting the program	GUI	Write the data to the default filename on command (perhaps File > Save to the default filename)
	18	NS			6	5	4	8	205	PB	allow the users to load data explicitly via GUI	we can manage multiple stores in different files	GUI	Read the data from a user-selected file on command (perhaps File > Open)
	19	NS			6	5	4	8	213	PB	allow the users to save data to a specified name via GUI	we can manage multiple stores in different files	GUI	Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
	20	NS				5	5	13	226	PB / SA	view a report of orders per SA in the GUI	I can estimate the value of employees / / I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	21	NS				6	5	21	247	All	enable basic login by role and customize the GUI	we don't have options that don't apply to our roles	GUI	User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
	22	NS				6	5	13	260	All	enable copy and paste from text fields	we can save typing	GUI	Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
	23	NS				6	6	13	273	BC	view my bill (invoice) in the GUI	I can pay for my robots	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
	24	NS					6	8	281	BC	view my orders in the GUI	see what I have coming to me	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
	25	NS					6	8	289	SA	view a sales report in the GUI	I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	26	NS					6	8	297	PB	view a report of all orders in the GUI	I can manage the company	GUI	A basic text report is fine (perhaps Report > All Orders)
	27	NS					6	13	310	All	Add multi-level undo	Worry less about making mistakes	GUI	This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
	28	NS					21	331	BC	see a pie chart of a model's component costs	I can decide if I want a different model	GUI	Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
	29	NS					13	344	SA	create a bulk (2+) order for Customer via GUI	avoid proliferation of orders and paperwork	GUI	Allow more than one robot model (with respective quantity) on a single order
	30	NS					8	352	PM	hide robot parts via GUI	obsolete parts aren't accidentally used	GUI	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	31	NS					8	360	PM	hide robot models via GUI	obsolete robots aren't ordered	GUI	Mark robot models as “obsolete” and don't allow adding them to new orders
	32	NS					21	381	SA	save a draft order and return to it later via GUI	I can multi-task between indecisive customers	GUI	Save an order that hasn't been complete, and allow SA to resume work on it later
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Sprint_1_Backlog_(1)
Sprint #	1
Start on	3/21/17 12:00 AM
End on	3/28/17 12:00 AM
Demo on	TBD

Total Tasks	16
Day 1 Left	16
Day 2 Left	16
Day 3 Left	16
Day 4 Left	16
Day 5 Left	16
Day 6 Left	9
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	Create_Parts	UML	CLI	KY	Create a use-case diagram	Complete
2	Create_Parts	UML	CLI	KY	Create a class diagram	Complete
3	Create_Parts	code	CLI	KY	Declare Robot Part class in part.h	Complete
4	Create_Parts	code	CLI	KY	Define a Robot Part class in part.cpp	Complete
5	Create_Parts	code	CLI	KY	Create a Makefile	Complete
6	Create_Parts	code	CLI	KY	Create a PM controller for part creation	Complete
7	Create_Parts	code	CLI	KY	Declare Arm class in arm.h	Complete
8	Create_Parts	code	CLI	KY	Define an Arm class in arm.cpp	Complete
9	Create_Parts	code	CLI	KY	Declare Battery class in battery.h	Complete
10	Create_Parts	code	CLI	KY	Define a Battery class in battery.cpp	Complete
11	Create_Parts	code	CLI	KY	Declare Locomotive class in locomotive.h	Complete
12	Create_Parts	code	CLI	KY	Define a Locomotive class in locomotive.cpp	Complete
13	Create_Parts	code	CLI	KY	Declare Head class in head.h	Complete
14	Create_Parts	code	CLI	KY	Define a Head class in head.cpp	Complete
15	Create_Parts	code	CLI	KY	Declare Torso class in torso.h	Complete
16	Create_Parts	code	CLI	KY	Define Torso class in torso.cpp	Complete
Sprint 1 Burn Chart
Tasks
Days

## Sprint_2_Backlog_(2)
Sprint #	2
Start on	3/28/17 12:00 AM
End on	4/5/17 12:00 AM
Demo on	TBD

Total Tasks	9
Day 1 Left	9
Day 2 Left	9
Day 3 Left	9
Day 4 Left	9
Day 5 Left	8
Day 6 Left	5
Day 7 Left	3

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	Create_Models	code	CLI	KY	Create a Robot Model class header file	Complete
2	Create_Models	code	CLI	KY	Define "setters" for Robot_Model in cpp file	Complete	torso, head, battery1, battery2, locomotor, arm1, arm2, name, price
3	Create_Models	code	CLI	KY	Define "getters" for Robot_Model in cpp file	Complete	total cost, price, torso, battery1, battery2, arm1, arm2, head, locomotor
4	Create_Models	code	CLI	KY	Create a menu for users	Complete	options: models or parts being created; models or parts listed; models or parts edited
5	Browse_Catalog	code	CLI	KY	Create view of vector of created models for BC	Started
6	Browse_Catalog	code	CLI	KY	Create a view of vector of parts for the PM	Started
7	Browse_Catalog		CLI	KY	Create a way to edit exisiting parts using CLI	NS
8	Create_Parts		CLI	KY	Create a way to add new Robot parts using CLI	Complete
9	Create_Models		CLI	KY	Create a way to add new Robot models using CLI	Started

					0
Sprint 2 Burn Chart
Tasks
Days

## Sprint_3_Backlog_(3)
Sprint #	3
Start on	4/4/17 12:00 AM
End on	4/11/17 12:00 AM
Demo on	TBD

Total Tasks	38
Day 1 Left	38
Day 2 Left	38
Day 3 Left	38
Day 4 Left	38
Day 5 Left	30
Day 6 Left	26
Day 7 Left	26

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	Browse_Catalog			KY	Design way to view the vector of models through CLI
2	Create_Models			KY	Design way to add new Robot Models through CLI
3	Create_Models			KY	Design way to edit existing models through CLI
4	New_Customer			KY	Declare a Customer class in header file	Complete
5	New_Customer			KY	Add Customer constructor	Complete
6	New_Customer			KY	Define Customer class getters in cpp file	Complete
7	New_Customer			KY	Define Customer class setters in cpp file	Complete
8	New_Customer			KY	Add vector of Customers into the Shop class	Complete
9	New_Customer			KY	add getter of Customers vector in Shop class
10	New_Customer			KY	Add “add Customer” method to the Shop class
11	New_Associate			KY	Declare a Sales Associate class in a header file	Complete
12	New_Associate			KY	Create S.A. constructor	Complete
13	New_Associate			KY	Define S.A. getters in cpp file	Complete
14	New_Associate			KY	Define S.A. setters in cpp file	Complete
15	New_Associate			KY	Add vector of S.A.’s into the Shop class
16	New_Associate			KY	Define getter for the S.A.’s in the Shop class
17	New_Associate			KY	Add “add Sales Associate” method in Shop class
18	New_Customer			KY	Design way to print list of Customers
19	New_Associate			KY	Design way to print list of Sale’s Associates
20	New_Order			KY	Declare Orders class in a header file	Complete
21	New_Order			KY	Define Orders constructor	Compelte
22	New_Order			KY	Define Orders getters methods	Complete
23	New_Order			KY	Define Orders setters methods	Complete
24	New_Order			KY	add Orders vector to the Shop class
25	New_Order			KY	define Orders getter in the Shop class
26	New_Order			KY	Add “new Order” method in the Shop class
27	New_Order			KY	Design way to print list of all the Orders
	Save_History			KY	Add save method to Part class
	Save_History			KY	Add save method to arm class
	Save_History			KY	add save method to torso class
	Save_History			KY	add save method to locomotor class
	Save_History			KY	add save method to head class
	Save_History			KY	add save method to battery class
	Save_History			KY	add save method to robot model class
	Save_History			KY	add save method to shop class
	Save_History			KY	add load method to shop class
	Save_History			KY	add save method to sales associate class
	Save_History			KY	add save method to customer class
	Save_History			KY	add overloaded constuctors to all classes for saving
Sprint 3 Burn Chart
Tasks
Days

## Sprint_4_Backlog_(4)
Sprint #	4
Start on	4/10/17 12:00 AM
End on	4/17/17 12:00 AM
Demo on	TBD

Total Tasks	29
Day 1 Left	29
Day 2 Left	29
Day 3 Left	29
Day 4 Left	29
Day 5 Left	29
Day 6 Left	29
Day 7 Left	29

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	Browse_Catalog		cli	KY	Design way to view the vector of models through CLI	Started
2	Create_Models		cli	KY	Design way to add new Robot Models through CLI	Started
3	Create_Models		cli	KY	Design way to edit existing models through CLI	NS
4	New_Customer		cli	KY	add getter of Customers vector in Shop class	NS
5	New_Customer		cli	KY	Add “add Customer” method to the Shop class	NS
6	New_Associate		cli	KY	Add vector of S.A.’s into the Shop class	NS
7	New_Associate		cli	KY	Define getter for the S.A.’s in the Shop class	NS
8	New_Associate		cli	KY	Add “add Sales Associate” method in Shop class	NS
9	New_Customer		cli	KY	Design way to print list of Customers	NS
10	New_Order		cli	KY	add Orders vector to the Shop class	NS
11	New_Order		cli	KY	define Orders getter in the Shop class	NS
12	New_Order		cli	KY	Add “new Order” method in the Shop class	NS
13	New_Order		cli	KY	Design way to print list of all the Orders	NS
14	Save_History		cli	KY	Add save method to Part class	NS
15	Save_History		cli	KY	Add save method to arm class	NS
16	Save_History		cli	KY	add save method to torso class	NS
17	Save_History		cli	KY	add save method to locomotor class	NS
18	Save_History		cli	KY	add save method to head class	NS
19	Save_History		cli	KY	add save method to battery class	NS
20	Save_History		cli	KY	add save method to robot model class	NS
21	Save_History		cli	KY	add save method to shop class	NS
22	Save_History		cli	KY	add load method to shop class	NS
23	Save_History		cli	KY	add save method to sales associate class	NS
24	Save_History		cli	KY	add save method to customer class	NS
25	Save_History		cli	KY	add overloaded constuctors to all classes for saving	NS
26	GUI_Window		GUI	Ky	move all “views” to a new CLI Class	Started
27	GUI_Window		GUI	KY	create window widget using fltk and get running	NS
28	GUI_Parts		GUI	KY	Create menu bar	NS
29	GUI_Parts		GUI	KY	Create “Create” submenu and add Parts option	NS
Sprint 3 Burn Chart
Tasks
Days